# Media Pluralism — Failure Modes Register (open)

Live risks in the outlet registry. Re-evaluated 14 September 2026. Nothing here is fixed — fixed items are in Fixed_Issues.docx.

OPEN  needs the action stated.   GUARDED  the risk is real; a documented check or rule catches it.   BY DESIGN  a deliberate limit, recorded so it is planned for.

Entry IDs are stable across both files — CLAUDE.md and OPEN_QUESTIONS.md cite them.

# A. The data as it stands

## A3 — Six Swiss outlets still carry UNVERIFIED DOMAIN notes

What: SonntagsZeitung, Le Matin Dimanche, La Liberte, Arcinfo, Luzerner Zeitung, Blick am Abend - 20 rows.

Why: These are the rows most likely to hold a wrong domain.

Spot it: Filter notes for UNVERIFIED.

Status: OPEN — SonntagsZeitung has documentary evidence (see A1). The rest resolve from domain_evidence_switzerland.tsv once the last 78 unanswered rows are re-run; human columns are in place to record the verdicts.

## A4 — One domain carries several outlets

What: 20 Minuten and 20 Minutes share 20min.ch; SonntagsBlick resolves to blick.ch; Le Matin Dimanche to lematin.ch.

Why: The pipeline fetches by domain, so their corpora merge and a measured position becomes a blend.

Spot it: wayback_identity.py marks these rows 'shared'. Group the CSV by domain.

Status: OPEN — Berk decides — OPEN_QUESTIONS.md #10. The tool confirms the domain; it cannot say whose articles are on it.

# B. Wayback and the CDX API

## B1 — The name-search index stops at 2016

What: web.archive.org/__wb/search/anchor is the only name-to-domain search; every result caps at 2016.

Why: Scope is 2016 onward, so it cannot resolve any rebrand in range.

Spot it: last_captured = 2016 on a site that plainly still exists.

Status: GUARDED — Discovery leads with brand-string change and capture discontinuity (CLAUDE.md §14a–b), which need no index.

## B3 — matchType changes the answer

What: domain times out on huge hosts; host returns 0 where exact returns captures.

Why: A zero from the wrong matchType looks like a real absence.

Spot it: Re-run any zero under a second matchType.

Status: GUARDED — Large hosts use exact (LARGE_HOSTS list); rule in §13.

## B6 — The imprint path varies by site and country

What: 20min.ch/impressum exists; blick.ch/impressum has no captures. Swedish sites use /om-oss, /ansvarig-utgivare.

Why: A single hardcoded path gives false negatives on the strongest evidence type.

Spot it: No captures at one path.

Status: GUARDED — Per-country path list in §20; fall back to the archived homepage's links.

## B8 — Archive.org goes down, and actively refuses connections under sustained load

What: Hours-long outages, rate limits of 4–11 queries/min, and — new on 14 Sep — outright refused connections after ~90 minutes of sweeping.

Why: A script that keeps going records the outage as data.

Spot it: HTML where CDX text was expected; 'connection refused'.

Status: GUARDED — wayback_identity.py stops after six refusals; default delay raised to 2s; --retry resumes without redoing settled rows.

# C. Identity — attributing a domain to the wrong outlet

## C1 — A domain outlives its publication

What: blickamabend.ch is archived through 2026; the paper folded in 2018.

Why: 'The domain existed' is close to worthless as evidence.

Spot it: Domain active life vs the brand's DNR appearances.

Status: GUARDED — Identity check per year, not existence.

## C2 — Two plausible domains, both live

What: 20minuten.ch and 20min.ch are both archived across the range; only 20min.ch publishes (1.5M pages vs 45).

Why: Name-matching picks one at random.

Spot it: Compare article counts.

Status: GUARDED — wayback_identity.py counts distinct article URLs per domain-year.

## C3 — A redirect is not proof of a rebrand

What: Old → new redirect is consistent with a rebrand, a domain sale, or parking.

Why: Tier A2 is only as strong as the confirmation of the target.

Spot it: Redirect target not yet confirmed for the outlet.

Status: GUARDED — Rule in §16: A2 alone only when the target is already confirmed; else Tier B.

## C4 — The aggregator/outlet boundary is a judgement call

What: Teletext and GMX are clearly aggregators; a portal with some original reporting is neither.

Why: Misclassifying injects other newsrooms' articles into an outlet's measured position.

Spot it: Bylines and imprint at the year in question.

Status: OPEN — Berk sets the threshold before country three — OPEN_QUESTIONS.md #3.

## C5 — Merging two outlet_ids is irreversible in practice

What: Two outlets under one id pool their articles; nothing downstream detects it.

Why: It surfaces, if ever, as an unexplained result in a paper.

Spot it: An outlet_id whose brand strings vary substantially.

Status: GUARDED — Standing rule: prefer the reversible error — keep ids separate when identity is unconfirmed.

# D. Reading the PDFs

## D2 — Bars carry two series in some editions

What: 2016: weekly + main source. 2017–2025: weekly + 3-days-plus. 2026: solid.

Why: The inner segment also descends, so a mis-read passes every check.

Spot it: The legend on the page.

Status: GUARDED — Table in §5, corrected once already (F3/H3). Read the legend, not the table.

## D3 — Chart order flips between editions

What: German pair on top 2016–2022, French from 2023.

Why: Reading by position swaps two markets for a whole year.

Spot it: The chart heading.

Status: GUARDED — §5: read the heading; where none (2020), the legend colour.

## D5 — A clipped crop looks complete

What: Happened on 2020, 2021, 2022 (Swiss) and 2026 (Swedish).

Why: Rows silently missing.

Spot it: Count bars on the full page; compare to rows after.

Status: GUARDED — Rule in §7. The validator cannot catch this.

## D6 — The DNR rewords one survey item across years

What: Swiss commercial TV appears under four labels 2016–2026.

Why: Split = broken series; merge = a judgement.

Spot it: Group category rows by concept.

Status: OPEN — Merged under one cat_ id with a note. Berk confirms — OPEN_QUESTIONS.md #5.

## D7 — Typos are kept on purpose

What: 'French commerical TV news', 'Le Journa', 'Le Matin ( incl Sunday Edition)'.

Why: Correct per spec; any join on brand will fail.

Status: BY DESIGN — Join on outlet_id, never brand.

# E. Structural

## E1 — Reuters changes URLs and layouts

What: URL pattern changed several times; three distinct layout eras.

Why: Links rot; crop bands go stale.

Spot it: Re-run dnr_pdfs/urls.txt; 404s.

Status: GUARDED — Verified 12 Sep 2026. Re-verify each new edition.

## E2 — CC-MAIN is not CC-NEWS

What: The acceptance test ran against CC-MAIN; the project's source from 2016 is CC-NEWS.

Why: Counts are directional, not coverage estimates.

Status: GUARDED — Noted in §18. Re-run against CC-NEWS when that pipeline exists.

## E3 — outlet_id namespace across 26 countries

What: Foreign outlets keep their own prefix (usa_cnn) so they recur across files.

Why: A shortname collision between markets.

Spot it: One id mapping to unrelated brands.

Status: OPEN — No collisions yet. Rule needed before country three.

## E4 — Multilingual markets are only partly surveyed

What: No Italian-speaking Swiss list in any year; RSI never appears.

Why: Structural incompleteness from the source. Same will apply to Belgium, Canada, Spain.

Spot it: Submarkets in data vs the country's language regions.

Status: BY DESIGN — Accepted; flag in any write-up.

## E5 — Category rows can never be fetched

What: ~25% of every list is an aggregate label with no domain.

Why: Real reach with no content behind it.

Spot it: Sum reach by brand_type per chart.

Status: OPEN — Kept and flagged. Berk decides the weighting — OPEN_QUESTIONS.md #1.

## E7 — Public-broadcaster sub-figures must not be summed

What: RTS TV 48% + Radio 32% against a headline of 63%.

Why: Summing inflates reach by a quarter.

Status: GUARDED — Kept in notes, not in weekly_reach_pct. OPEN_QUESTIONS.md #8.

## E8 — Nothing is committed

What: Everything is untracked on a protected main.

Why: No backup, no review, and the longest-standing item in this file.

Spot it: git status.

Status: OPEN — Branch data/changing-column-types, commit, push, PR. Commands in WORKING_MANUAL.md §4.

# F. Limits of the documented method

## F1 — The page finder is a heuristic

What: Three rewrites to get Switzerland right; then it returned Switzerland's page for Sweden 2020 (H1).

Why: A wrong page yields a complete, validator-passing dataset for the wrong country.

Spot it: The chart page must name YOUR country, not merely have charts.

Status: GUARDED — H1 fixed; rule in §2. Verified on Switzerland, Sweden, Germany.

## F2 — Crop bands are starting points, not geometry

What: Swiss bands are for a four-chart layout; Sweden needed custom bands every year. Even Swiss 2016–2021 needed adjustment. (Absorbs G4, H7.)

Why: A band that reads as authoritative clips a list, and a clipped list looks complete.

Spot it: Count bars before cropping.

Status: GUARDED — §7 now labels the table as starting points and withdraws the transferability claim.

## F5 — Archive.org throughput caps the roll-out

What: 4–11 queries/min, throttling after sustained load. A country needs ~250 liveness + ~500 identity requests.

Why: About an hour per country of wall-clock, before human review.

Spot it: Measure; don't estimate — early estimates were off by 10× both ways.

Status: OPEN — Plan for it; cache foreign-domain results across countries (H12).

## F6 — Identity verification is deliberately not autonomous

What: Rebrand vs sale, shared domains, an outlet's name on someone else's site — all referred to a human.

Why: Throughput-bound by review time.

Spot it: Count needs-human + shared rows per country.

Status: BY DESIGN — §21. Switzerland: ~10–12 outlets.

## F7 — The finder uses the extraction we distrust elsewhere

What: find_country_pages.py locates pages via pdftotext.

Why: 'Not found' can mean extraction failed, not that the country is absent.

Spot it: A 'not found' for a country plainly in the report.

Status: BY DESIGN — Acceptable: it only locates; every number is read from the image.

## F8 — Country names change between editions

What: The finder matches a literal string.

Why: A rename shows as 'not found' for those years.

Spot it: Some years resolve, others don't.

Status: GUARDED — Try the edition's spelling.

## F9 — Appendix A turns a re-run into a confirmation

What: CLAUDE.md carries the verified Swiss answers.

Why: An agent that reads them reproduces rather than tests.

Status: GUARDED — Blind runs are given the method without the appendix and state so. Both runs to date were blind.

# H. Sweden reusability run, 13 September

## H6 — The 'ALSO' box of partisan brands, 2018–2020

What: Fria Tider, Nyheter Idag, Samhällsnytt and others printed beside the online chart, not as bars, not in order.

Why: Exactly the outlets a pluralism measure needs; excluding them leaves a 2018–2020 hole.

Spot it: A boxed list with percentages beside the online chart.

Status: OPEN — Excluded; values preserved. Berk decides — OPEN_QUESTIONS.md #9.

# K. Findings from the human review of Switzerland 2016, 15 September

## K1 — Language editions live at a path on a shared domain

What: French 20 Minuten is 20min.ch/ro/ (Romandie). Bluewin serves bluewin.ch/de/ and bluewin.ch/fr/ with a language toggle. The registry records only the registered domain, per the RA spec.

Why: Extraction fetches by domain and gets both editions mixed, with nothing to attribute an article to che_20min_fr. The identity check confirms the German homepage and marks the French row 'shared'.

Spot it: A shared domain whose homepage renders in one language for a two-language market.

Status: OPEN — Proposed: an edition_path column (open question 10). Until then, note the path in human_note.

## K2 — teletext.ch renders German only; the French edition's location is unknown

What: The DNR lists Teletext for French-speaking respondents too, but teletext.ch shows SRF's German service. Whether the French (RTS) teletext sits at a path on teletext.ch or on another host is unverified - Archive.org was throttling when checked.

Why: If it is on another host, the French che_teletext rows carry the wrong domain.

Spot it: The French rows for an outlet whose domain renders only in German.

Status: OPEN — Check teletext.ch/fr and rts.ch for a teletext path when Archive.org allows.

## K3 — lematin.ch's late-2016 capture renders as an e-paper

What: The 26 Dec 2016 capture of lematin.ch looks like an e-paper page rather than a news site.

Why: Same pattern as SonntagsZeitung: branded correctly, articles possibly elsewhere. Could also be a holiday landing page caught by one capture.

Spot it: An A3 or shared verdict whose archived page is an e-paper shop, not headlines.

Status: OPEN — Check a mid-2016 capture before concluding. If it is an e-paper there too, Le Matin's articles lived elsewhere in 2016 and the rows need the SonntagsZeitung treatment.

## K4 — A single Wayback capture is not the year

What: One capture (26 Dec) suggested lematin.ch was an e-paper in 2016; the year had hundreds of captures and the mid-year ones may show a news site.

Why: Judging a whole year from one capture - especially a holiday one - misreads sites that change over the year or serve special pages on particular days.

Spot it: A surprising verdict from a capture dated near a holiday or a redesign.

Status: GUARDED — Look at two or three captures spread across the year before recording a verdict. The identity script uses the capture nearest 1 July for this reason.

# I. Identity tooling, 14 September

## I3 — The masthead match is a heuristic with an unmeasured false-positive rate

What: A keyword in the title confirms branding, not that this is the right outlet among similarly-named ones.

Why: The argument for reviewing only failures rests on the passes being trustworthy.

Status: OPEN — Hand-check a random 30 A3 rows before proposing reduced review to Berk.

## I4 — Identity tooling cannot decide rebrand vs sale, or whose articles are on a shared domain

What: A3 confirms a host presented itself as the outlet; A2 (redirect) and shared-domain attribution stay manual.

Why: The residual human work is real and should be planned, not discovered.

Spot it: needs-human and shared rows.

Status: BY DESIGN — §21 and §19. See F6.

# How to use this file

Add an entry whenever something is found wrong or a step turns out to rest on an assumption.

When an entry is fixed, move it to Fixed_Issues.docx under the same ID — do not delete it.